Interventionist Manual of Procedures

Version 1, March 2011

MARYLAND

HEALTHY STORES

Providing & Promoting Healthy Food Choices

DRAFT - DO NOT DISTRIBUTE

CONTENTS

INTERVENTION MANUAL OF PROCEDURES

WELCOME TO MARYLAND HEALTHY STORES

Mission Statement

Interventionist Responsibilities and Duties

Policy Issues

INTERVENTION PLAN

Overview of Intervention Plan

Phase 1: 	HEALTHY BEVERAGES

Phase 2: 	HEALTHY SNACKS

Phase 3: 	HEALTHY HOME FOOD PREPARATION

Phase 4: 	HEALTHY DELI AND CARRY-OUT FOODS

SUMMARY of foods & behaviors promoted in each phase

Interventionist work plan

Intervention materials standards

STORE ASSIGNMENTS & GENERAL GUIDELINES

Stores interventionist assignments- TBD

Guidelines for working in small stores

PROMOTED FOODS

Working with store partners to stock foods

Food promotion list

COMMUNICATION MATERIALS

SHELF LABELS

Description of shelf labels and instructions for use

Promoted food shelf label list

POSTERS

Guidelines for using posters

Posters by phase

FLYERS

Guidelines for flyer use

Flyers by phase

EDUCATIONAL DISPLAYS

Guidelines for educational display use

Sample educational displays

MATERIALS FOR STORE OWNERS

Store Owner Schedule

MHS FAQ sheet for store owners (TBD)

MASS MEDIA (TBD)

INTERVENTIONIST WEEKLY PLANS BY PHASE

COOKING DEMONSTRATIONS AND TASTE TESTS

General information about cooking demos and taste tests

Phase 1: Healthy beverages taste tests

Phase 2: Healthy snacks taste tests

Phase 3: Healthy home food preparation cooking demo and taste tests

Phase 4: Healthy carry out taste tests

GIVEAWAYS

INCENTIVE GIFT CARDS

PROCESS EVALUATION

Description of process evaluation components

Table of evaluation components

Process evaluation manual of procedures

APPENDIX A: Interventionist Log and Process Evaluation form

Interventionist Log

Process Evaluation Form

NOTE:

This document has been a work in progress since the start of the project and will be revised and expanded throughout the completion and evaluations of the Maryland Healthy Stores project in 2011.  DO NOT COPY OR DISTRIBUTE THESE MATERIALS TO ANYONE WITHOUT PERMISSION.

COPYRIGHT 2009-2010 JOHNS HOPKINS CENTER FOR HUMAN NUTRITION.

MARYLAND HEALTHY STORES PROJECT TEAM:

Dr. Joel Gittelsohn, Principal Investigator, Johns Hopkins Center for Human Nutrition

Present team:

Megan Rowan, Senior Research Coordinator, Johns Hopkins School of Public Health

Donna Dennis, Research Assistant, Johns Hopkins School of Public Health

Harmony Farner, Research Assistant, Johns Hopkins School of Public Health

Linda Thomas, Lead Interventionist, FISS Program Manager, Charles County Department of Health

Linda Abell Blake, Interventionist, Division Director, Charles County Department of Health

Erin Penniston, DHMH Project Coordinator, Childhood Wellness Coordinator, Maryland DHMH

Amanda Wilcox, DHMH Project Collaborator, Maryland DHMH

MISSION

MARYLAND HEALTHY STORES

The Maryland Healthy Stores Program seeks to improve the availability of healthy food options at local stores and to promote these foods both at the point of purchase. This program has the intention of improving the nutritional content of foods purchased and consumed by the population and doing so in a way that the changes made can be sustained after the project is complete.

HEALTHY STORES PROGRAMS

The Maryland Healthy Stores program is part of several Healthy Stores programs which are intended to improve the availability of healthy foods, promote them at the point of purchase, and improve local food systems in general to disadvantaged populations throughout the United States and other select populations. Maryland Healthy Stores is one of 4 current Healthy Stores projects in Maryland, including Healthy Bodies, Healthy Souls (HBHS), Baltimore Healthy Eating Zones (BHEZ), and Baltimore Healthy Carryouts (BHC). To date, completed Healthy Stores programs include two rounds of intervention in Baltimore City (completed in 2008), a pilot trial in the Republic of the Marshall Islands, a one-year intervention with the Apache (completed in July 2004), and an intervention with consumers, food retailers, producers and distributors in Hawaii (Healthy Foods Hawaii). A project with First Nations Communities in Canada (Zhiiwaapenewin Akino’maagewin: Teaching to Prevent Diabetes) (ZATPD) Round 1 was completed in 2006 and Round 2 in the comparison communities is ongoing. The Apache Healthy Stores Project (AHS) is being re-initiated as Apache Healthy Foods (AHF) in collaboration with the Tribal Diabetes Prevention Program in the 2 reservations. The Navajo Healthy Stores (NHS) Project is an extension of AHS program on the Navajo Nation, and is currently in the post-intervention evaluation stage. The Baltimore Healthy Eating Zones project is also currently in the post-intervention evaluation stage.  Check our website at www.healthystores.org for up-to-date information.

POLICY & PUBLIC RELATIONS ISSUES

As the person associated with the Maryland Healthy Stores project with the greatest contact with the public, the Interventionist will frequently have to deal with the public and multiple requests for information.  This section is intended to give you guidance for the most common issues you are likely to face:

Requests for Materials:  It will not be possible to pass out materials until the study has been completed and evaluated. At this point materials for similar healthy stores studies will be available for dissemination and use through our website (www.healthystores.org).

PRESS Requests:  Contact Dr. Joel Gittelsohn (Principal Investigator), Associate Professor, Center for Human Nutrition, Johns Hopkins Bloomberg School of Public Health, Phone: 410-955-3927, Email: jgittels@jhsph.edu

INTERVENTION PLAN

INTERVENTIONIST RESPONSIBILITIES & DUTIES

This section of the Manual of Procedures lists the primary responsibilities of the Interventionist.  More information on specific interventionist responsibilities is included in later sections of this manual.  NOTE: The interventionist should make a timeline of events outlining what needs to happen and where. Doing this before the intervention begins will help you organize and be prepared to fulfill all of your responsibilities.

The Interventionist is responsible for all of the different components of the MHS program in his or her assigned store(s).  The interventionist will:

- STOCKING OF FOODS: Make sure each store has stocked the promoted foods during the appropriate phase of the Maryland Healthy Stores (MHS) project.

*See Maryland Healthy Stores Food Promotion List p.39

- SHELF LABELS: Make sure the store has the appropriate shelf labels up for each of the promoted foods at the appropriate times.

*See Promoted Food Shelf Label List, p. 42

- POSTERS: Put up and maintain posters for each of the promotional phases.

- FLYERS: Make sure stores have an adequate number of flyers to be handed directly to customers or given out in shopping bags. Hand out flyers to customers during the cooking demonstrations.

- STORE OWNER MATERIALS: Provide MHS FAQ sheet to store owners and answer questions they have about participation.

- COOKING DEMONSTRATIONS/TASTE TESTS: Set up, conduct and clean up after cooking demonstrations and taste tests at each of the assigned intervention stores. Complete Cooking Demonstration/Taste Test Log for every one conducted.

- GIVEAWAYS: Hand out giveaways and other promotional items at the stores.  This will usually be tied to specific cooking demonstrations and taste tests. See Giveaways, p. 87

- BUTTONS: These should be distributed along with the giveaways during the intervention of the respective phases.

- GIFT CARDS: Provide gifts cards for store owners to purchase promoted food items.

- NUTRITION INFORMATION: Be prepared to answer questions about nutrition and the function of the Maryland Healthy Stores project.

- PUBLIC RELATIONS: Represent the project in a professional manner.

  - Maintain good relationships with all intervention store staff and managers.

  - Meet briefly with each store manager to update them weekly.

  - Respond appropriately to feedback about the MHS project.

- REPORTS AND FORMS: Complete Interventionist Logs to document program activities.

OVERVIEW OF INTERVENTION PLAN

The Maryland Healthy Stores intervention has the aim of promoting consumption of healthy foods through a store-based promotion program. The table below outlines the lessons or phases in each component.

TABLE OF PHASES FOR MHS

| Phase | NAME OF THE PHASE | DATES |
| --- | --- | --- |
| 0 | TEASER | 4/25/11-4/29/11 |
| 1 | HEALTHY BEVERAGES | 5/2/11-6/3/11 |
| 2 | HEALTHY SNACKS | 6/6/11-7/8/11 |
| 3 | HEALHY HOME FOOD PREPARATION | 7/5/11-8/12/11 |
| 4 | HEALTHY DELI/CARRYOUT FOODS | 8/15/11-9/16/11 |

PHASE 0:

TEASERS

THEMES	Kickoff

MESSAGES	Introducing the new Maryland Healthy Stores program

FOODS	None

BEHAVIORS	Increasing awareness of MHS program in local stores

Building anticipation for the MHS program

SHELF LABELS 	None

COOKING DEMO/

TASTE TEST  	None

EDUCATIONAL

DISPLAY 	None

POSTERS	Coming to this store…Maryland Healthy Stores

FLYERS	None

GIVEAWAY	None

BUTTONS                 None

CORNER STORE	Store Owner Recruitment/Training: Store FAQ Sheet

PHASE 1:

HEALTHY BEVERAGES

THEMES	Drinking Lower-Calorie Drinks

MESSAGES	Low-calorie drinks are healthier

BEVERAGES 	Water

Diet Soda

Sugar-Free drink mixes

100% Juice (not included in taste-testing)

Low-Fat Milk

BEHAVIORS	Choosing healthier drinks

SHELF LABELS  	Lower in Sugar

Lower in Fat

COOKING DEMO/

TASTE TEST 	Low calorie drink taste test

- Diet sodas (Coke Zero, Sprite Zero, Diet Dr. Pepper, Diet Canada Dry, Diet Mountain Dew)

- Sugar free drink mix

- Low fat milk (2%, 1%, skim)

EDUCATIONAL        Quench Your Thirst with Water/Water does the body good (see SAMPLE)

DISPLAYS

POSTERS	What are you really drinking? (see SAMPLE)

Drink 100% Juice. You deserve it. (see SAMPLE)

Whole milk is 50% fat

FLYERS  	What are you really drinking? (May be poster or flyer)

After 2, you can go blue

GIVEAWAYS	No Sugar Added Water Bottle with MHS Logo (see SAMPLE)

Crystal Light packets

BUTTONS	MHS logo

No Sugar Added

TBD

STORE	$50 gift cards to store owners for diet sodas, Crystal Light, and LF milk

Phase 2:

HEALTHY SNACKS

THEMES	Healthy snacks

High fiber as snacks

MESSAGES	Try fruits and veggies for a healthy snack

Baked chips, pretzels, and seeds are healthier snacks

FOODS 	Fruits (fresh, dried [unsweetened], fruit cup/can in 100% juice or light syrup)

Reduced fat chips, baked tortilla chips, and pretzels

Veggies with low-fat dip

Low-fat granola bars or trail mix

BEHAVIORS	Eat fruits or vegetables for snacks

Try new ways to eat fruits and vegetables

Choose baked instead of fried snacks

SHELF LABELS 	Lower in Fat

Lower in Sugar

Healthy Choice

High Fiber

TASTE TEST 	Baked chips and pretzels

Fresh fruit

Granola bars/trail mix

EDUCATIONAL       Make lifelong changes (Old. TBD)

DISPLAY                  (See SAMPLE)

POSTERS

Baked for better health/baked is better (TBD)

How many fruits and vegetables have you had today?

Have a Snack Attack without the Fat (Old; TBD)

Flyers 	Baked vs. regular chips vs pretzels (TBD)

Fill up with fiber

GIVEAWAYS	Magnet

Buttons

Chip clips/Samples of promoted snacks)

Fresh Fruit

BUTTONS                 MHS Button

Strive for 5, etc. (TBD)

STORE                     $50 gift card for food purchases
PHASE 3:

HEALTHY HOME FOOD PREPARATION

THEMES	Healthy Cooking at Home

Pack a healthy lunch

Know portion size

MESSAGES	Use cooking spray for lower-fat cooking

Add vegetables to your meals

Bake instead of frying

Use whole wheat bread for sandwiches

FOODS	Cooking Spray

Whole wheat bread

Low-fat cheese

Low-fat mayo

Low-fat dressing

Vegetables

BEHAVIORS	Use cooking spray

Eat more vegetables

Choose whole wheat bread instead of white

Choose low-fat mayo over high-fat mayo

SHELF LABELS  	Lower in Fat

Healthy choice

Higher in fiber

COOKING DEMO/

TASTE TESTS              Pan-frying with cooking spray

Sandwich taste test

Vegetable with low-fat dressing taste test

EDUCATIONAL        Providing and promoting healthy choices for Maryland (TBD)

DISPLAY

POSTERS 	Forget the fried

Bake for better heath (TBD)

You are what you eat (TBD)

Eat more, die young (with single serving bowls)

FLYERS 	Eat well, Stay strong, Live long (cooking spray flyer) (Old; TBD)

How many fruits and vegetables have you had today? (TBD)

Three ways to reduce fat at home (Old; TBD)

GIVEAWAY             Buttons

Magnet

Single serving bowl

Measuring spoon

BUTTONS                  MHS Buttons

Strive for 5

A healthy lunch packs a punch (Old; TBD)

Forget the fried

STORE	$50 gift card to store owners to buy promoted foods

Phase 4:

HEALTHY DELI/CARRY-OUT FOODS

THEMES 	Lower fat deli/carry-out foods

MESSAGES	Choose lower-fat deli/carry-out options

Reduce the mayonnaise

Reduce fried foods

Choose whole wheat bread

FOODS	Whole wheat bread

Light mayonnaise/low-fat condiments

Water

Fruit

Low-fat chips and pretzels

BEHAVIORS	Choosing lower-fat deli/carry-out meals

Choosing light mayonnaise or other low-fat condiments

SHELF LABELS  	Lower in Fat

Higher in fiber

TASTE TEST               Light mayo on sandwich

POSTERS                 Hold the Mayo, your heart will thank you (OLD; TBD))

Baked for better health (TBD)

FLYER 	Make healthy carryout choices (OLD; TBD)

You are what you eat

GIVEAWAY	      Magnet

Samples of light mayonnaise

DELI/CARRY-OUT   Modified handout menu highlighting healthier options (see SAMPLE)

$50 gift to buy healthier foods

SUMMARY:

FOODS & BEHAVIORS

| Phase | Name of the phase | Promoted Behavior | Promoted foods | Giveaways/Handouts |
| --- | --- | --- | --- | --- |
| 0 | TEASER | Increasing awareness of MHS program in local stores Building anticipation for the MHS program Follow the 10% Rule | None | FAQ to store owner |
| 1 | Healthy beverage | Choose healthier and low calorie drinks, water, diet sodas and low-fat milk | Diet Sodas : Diet Pepsi, Pepsi One, Sprite Zero, etc.)) 100% Fruit Juice Water Low-calorie drink mix (Crystal Light, Wyler's Light) | Water bottles Crystal light Magnets Buttons Flyers |
| 2 | Healthy Snacks | Eat fruits or vegetables for snacks Try new ways to eat fruits and vegetables Choose baked instead of fried snacks Try high fiber snacks | Fruits: Apple, bananas, oranges Vegetables: Celery, Carrots Low Fat Snacks: Baked Chips, Pretzels, Sun Chips, High Fiber: Granola Bars, trail mix, nuts, seeds | Chip Clips Magnets Buttons Flyers |
| 4 | Healthy Home Food Preparation | Use cooking spray Use low-fat condiments Buy healthier foods Add vegetables into cooked meals Pack a healthy lunch | Cooking Sprays Fresh/Canned/Frozen vegetables Whole wheat bread Low-fat mayonnaise Low-fat dressing | Measuring spoon Single Serving Bowls Light Mayo Packets Magnets Buttons Flyers |
| 5 | Carry-out | Choose lower-fat meals Request light mayonnaise on foods Choose whole wheat Choose healthier sides | Whole Wheat Bread Low fat and fat free mayonnaise, ketchup, mustard Healthy sides: fruits, vegetables | Light Mayo packets Magnets Buttons Flyers |

INTERVENTIONIST WORK PLAN

EVERY STORE VISIT:

- Complete the Interventionist Weekly Progress Report (See Appendix A for form).

IN THE WEEK BEFORE A PHASE BEGINS:

- Make sure store has stocked/ordered foods to be promoted.

- Make sure you have at least 25 copies of each flyer.

- Arrange with store manager for a space to conduct the cooking demonstrations/taste tests.

- Make sure you have all food (non-perishable) and materials needed for each cooking demonstration/taste test.

IN THE FIRST WEEK OF A PHASE:

- Put up the appropriate shelf labels for the foods being promoted.

- Put up all posters for that phase at stores.

- Complete the Interventionist Log when posting materials. (See Appendix A for forms.)

DURING THE PHASE:

- Check at least once a week to make sure promoted foods are in stock (if running low, and at early stage of promotion, ask manager / store owner to order more).

- Make sure the shelf labels are under the appropriate foods (sometimes food stocks are shifted around).

- Regularly check to make sure the posters are still up. Re-attach if they are falling down.

- Conduct an interactive session once per week.

- Hand out corresponding flyers and giveaways at each cooking demonstration/taste test.

- Complete the Interventionist Log when conducting activities. (See Appendix A for forms.)

AFTER THE PHASE HAS BEEN COMPLETED:

- Take down posters if needed to make room for new posters, but leave up shelf labels for promoted foods.

To fill out the Interventionist Log, the interventionist will follow these steps:

- Enter his/her name.

- Enter the date.

- Enter the name of the store.

- Check the number corresponding the current promotional phase.

- Check the number of peer educators present.

- Check off all activities conducted during the visit.

- Record the type of cooking demonstration or taste test (e.g. milk, chips, etc).

- Record where the cooking demo or taste test was done in the store (e.g. anteroom,     back of the store, outside).

- Enter start time.

- Enter end time (when completed).

- Record number of materials posted in the store during each visit (shelf labels, posters).

- Record number of materials distributed (flyers, buttons, giveaways).

- Describe activity details for the visit, including interactions with store owners and customers.

- Record attendance of visitors, marking tick marks as you go along, distinguishing between brief visitors (10 seconds to 1 minute) and longer visitors (greater than 1 minute, discussion) and grouped by age and gender.

- Record with tick marks/tallies the number of food samples, flyers and giveaways handed out during the cooking demo or taste test.

- Record questions asked or comments made by customers participating in cooking demonstrations or taste tests.  This can be continued on the reverse side of the form.

- Turn in completed form to MHS office.

INTERVENTION MATERIALS STANDARDS

| Material/Intervention Component | Small stores | Delis/Carry-out restaurants |
| --- | --- | --- |
| Stocking of healthy food choices | Minimum of 5-10 units of the target foods stocked for the duration of their promotional phase | N/A |
| Posters | One of each developed for the phase posted in plain view; full size or reduced size Posted at the beginning of its phase Taken down at the end of the phase if needed | One of each poster appropriate for carryout restaurants (beverages and carryout) posted in plain view; full size or reduced size Posted at the beginning of its phase |
| Flyers | Minimum 25 passed out during cooking demonstrations/taste test per phase | N/A |
| Shelf labels | Post at the beginning of its phase, in stores where foods are accessible to consumers | N/A |
| Taste tests | Conducted a minimum of 6 times per promotional phase | N/A |
| Giveaways | Minimum 25 passed out during cooking demonstrations/taste test per phase | N/A |
| Buttons | Minimum 25 passed out during cooking demonstrations/taste test per phase | N/A |
| Carryout menu | N/A | Place on deli/carryout counter at the beginning of carryout phase |

Interventionist notes:

- Need to make sure materials are posted and remain up throughout their phase.

- The standards above are per store.

- If a particular phase does not have a specific type of material developed, the standard does not have to be met

GENERAL GUIDELINES FOR WORKING SMALL STORES

- Varying up the time that cooking demonstrations are held is useful to contact a variety of customers: conduct some on weekday, some on weekends, at different times.

- Offer for store owners to put up the posters for each phase themselves. This allows them to feel comfortable about posting materials, especially if space is limited in the store. If this option is used, check back on a later date to make sure owners have put up the posters.

- Post shelf labels under shelves so they do not take up space

- Make sure not to hide any WIC labels

- Space is limited, so be flexible about where you conduct taste-tests. You may choose to work at the back of the store, in an ante-room, of even outside if the weather is nice.

- Be considerate of the needs of the store owners. Many owners may feel uncomfortable about having other activities in the store due to theft, disruption, spilling of food, etc. Talking with the store owner about how to ease their worries will aid in planning for these activities.

- Customers in smaller stores may have little space to talk; handing out flyers and engaging in small discussions about the demonstrations can be helpful to engage them.

- Ask the store owner where to set up the table to be most convenient and will not block traffic.

- Some store owners may prefer that we don't distribute materials to the children. In such cases, do as the owner suggests and apologize for any inconvenience caused to them.

CORNER STORE MENUS AND SIGNS

Offering to create colorful menus and welcome signs for each of the corner stores is a way to improve rapport.  Interventionist may record menu offerings from the stores with delis/carryouts and have them graphically designed as color menus.  Those stores without deli/carryout options should be offered posters as welcome signs.  For phase 4, Deli/Carryout Foods, small symbols can be put next to the labels for the healthier choices on the menus, and encourages store owners to provide healthy options.  An example is shown below:

PROMOTED FOODS

FOODS TO BE STOCKED IN STORES

Working with store partners to stock foods

Store partners of the Maryland Healthy Stores project have agreed to stock specific minimum quantities of foods for promotion for specific phases of the intervention.

The interventionist needs to work with store managers and vendors to ensure that:

- the appropriate foods are ordered*

- the foods to be stocked are on the shelves

- promoted foods are visible when customers walk through the aisles

- promoted foods are labeled with MHS shelf labels

- promoted foods are priced appropriately (i.e. not more than less-healthy options)

The interventionist should make sure the promoted foods are stocked at the beginning of each phase and at least every other week during the phase. This should be done by direct observation.

The interventionist should provide the store owner with a list of the promoted foods for each phase during the prior phase. For instance, the list of snacks that will be promoted should be given to the store owner during Phase 0.

If the promoted foods are not available, the interventionist should immediately meet with the store manager/owner and/or vendor, discuss barriers to stocking the food, problem solve, and encourage them to stock the food.  The interventionist should talk to the store owner/manager about sales of the food, what could be done to enhance sales, such as positioning the food better.

The interventionist should encourage the store owners/managers to continue to stock the promoted foods AFTER the phase has been completed.

*The interventionist needs to make sure that stores do not substitute alternatives for the promoted foods.  For instance, Frosted Flakes are NOT an acceptable substitution for Corn Flakes.

NOTE: This is probably the single most important part of the store component. If we cannot get the stores to consistently stock promoted foods, we will not succeed.

PROMOTED FOODS BY PHASE

Maryland Healthy Stores

Food Stocking List (March 2011)

| Date | Food | Minimum needed per corner store |
| --- | --- | --- |
| PHASE 1: | Water | 10 units |
|  | Diet Soda | 5 units |
|  | Sugar-free drink mixes | 5 units |
|  | Low-fat (1% or skim milk) | 5 units |
|  | Calcium Fortified 100% juice | 5 units |
| PHASE 2: | Fruit* | 5 units |
|  | Vegetables* | 5 units |
|  | Baked chips/ reduced fat chips / pretzels | 5 units |
|  | Seeds, Nuts, and/or Trail Mix | 5 units |
| PHASE 3: | Cooking spray | 5 units |
|  | Fresh, canned, or frozen vegetables | 5 units |
|  | Low-fat cheese (if refrigeration is available) | 5 units |
|  | Low-fat mayo | 5 units |
|  | Low-fat dressing | 5 units |
|  | Whole wheat bread | 5 units |
| PHASE 4: | Wheat Bread | 5 units |
|  | Low-fat mayo | 1 large container |
|  | Low-fat cheese | 5 units |
|  | Poultry (not fried) | 5 units |
|  | Water | 5 units |

*can be fresh, frozen or canned (in 100% juice or light syrup only)

Local Produce

Many Charles County Stores have connections to local farmers.  Encourage them to work with those farmers to increase the stocking of fresh fruits and vegetables, and offer to work directly with the farmer to ensure availability, affordability, and delivery.

COMMUNICATIONS

MATERIALS

SHELF LABELS BY PHASE

| Phase/Date | Food | Shelf Label(s)* |
| --- | --- | --- |
| PHASE 1: | Water | LS, HC |
|  | Diet Soda | LS |
|  | Flavored water | LS |
|  | 100% fruit juice | HC |
|  | Low-fat Milk (1% or skim) | LF |
| PHASE 2: | Fresh, dried, or canned fruit, incl. fruit cups | LS, HC |
|  | Baked chips, Sun Chips, pretzels | LF |
|  | Granola Bars | HF, HC |
|  | Nuts, seeds, trail mix (no chocolate) | LS (seeds/nuts), HF, HC |
| PHASE 3: | Cooking spray | LF |
|  | Canned/Frozen/Fresh vegetables | HF, HC |
|  | Low-fat Dressing | LF |
|  | Low-fat Mayo | LF |
|  | Low-fat Cheese (TBD) | LF, HC |
|  | Whole wheat bread | HF, HC |
| PHASE 4: | Light/low-fat mayo | LF |
|  | Light dressing | LF |
|  | Low-fat cheese | LF, HC |
|  | Whole wheat bread | HF |

| *Shelf Labels Key |  |
| --- | --- |
| LS | Lower in Sugar |
| LF | Lower in Fat |
| HF | Higher in Fiber |
| HC | Healthy Choice |

Shelf labels

DESCRIPTION OF SHELF LABELS AND INSTRUCTIONS FOR USE

The interventionist is responsible for making sure the appropriate MHS shelf labels are up for every promoted food. The shelf labels are intended to serve as an easy reference for shoppers - to help them choose healthier alternatives over less healthy offerings in the food section. A SAMPLE shelf label from BHS is displayed here.

The following shelf labels have been developed:

Healthy food choice: intended to refer to an overall healthy food choice, not so much a direct alternative to other foods (i.e. fruits and vegetables)

Lower in sugar: intended to refer to a food choice which has substantially less sugar than foods in a similar category that are more commonly consumed (e.g. pastries). Usually <10 g sugar per serving.

Lower in fat: intended to refer to a food choice which has substantially less fat than foods in a similar category that are more  commonly consumed (e.g. low fat mayo). Usually <10% DV fat per serving.

Higher in fiber: intended to refer to a food choice which has substantially more fiber than foods in a similar category that are more commonly consumed (e.g. nuts). Usually <10% DV fiber  per serving.

Shelf labels from previous phases should stay up for the remainder of the intervention.  They should be checked up on with each new phase and replaced if damaged.

It is likely that items on the shelves may shift when foods are restocked and that the shelf label may no longer sit under the appropriate food. Therefore the interventionist should write the name of the promoted food in permanent black ink in block letters in the space at the bottom of the label.  The interventionist will need to check the label placement weekly and make sure labels are properly located, and shift them if necessary.  In smaller stores it may help to give the manager and store staff a list of the promoted food shelf labels.

Note: The interventionist should make sure she/he has the permission of the manager before making these adjustments.

Guidelines for

Using posters

About the posters:

Posters are one of the main mass media communication methods that are being used in the Maryland Healthy Stores program. Each phase of the MHS intervention has one or more posters that have been developed for that phase. Post the tabloid size posters (11”x17”) or flyers in smaller stores since space is limited and the smaller ones are less likely to be removed by store staff.

When to hang:

The appropriate posters must be put up in the first 3 days of the intervention phase. At the end of each promotional phase, the Interventionist will take down the old posters if necessary to make room for the new posters.

Locations:

They should be evenly divided between stores. The interventionist will need to get permission to put up the posters and select a suitable location at each site.

Documentation and Maintenence:

The interventionist will need to record when each poster is put up using Interventionist Log (see Appendix A).  The interventionist will need to monitor store posters to ensure that they are securely posted and re-hang posters that may have fallen or been torn down.  Damaged posters should be replaced. Old posters (in good condition) should be stored in the project office.

Posters by phase

Posters will be printed in various sizes depending on location.

NOTE: THESE ARE SAMPLES FROM BALTIMORE HEATHEY STORES AND BHEZ; THESE WILL NOT BE USED

PHASE 0 –TEASERS (SAMPLE ONLY)

PHASE 1 – HEALTHY BEVERAGES (SAMPLES ONLY)

PHASE 2:  HEALTHY SNACKS (SAMPLES ONLY)

PHASE 3: COOKING AT HOME/HEALTHY LUNCH AND BREAKFAST (SAMPLES ONLY)

PHASE 4: HEALTHY DELI/CARRYOUT (SAMPLES ONLY)

Using Flyers

Flyers are a form of educational material on which more information about a topic may be conveyed.  They are used in multiple ways in the Maryland Healthy Stores project:

Flyers may be handed out by the interventionist during cooking demos and taste tests, or handing out materials may be an activity in itself.

DOCUMENTATION AND MAINTENANCE

The interventionist will need to record where and when flyers are distributed using the Interventionist Log (see Appendix A).  The interventionist will need to ensure that he/she has enough flyers available at each site and that they are appropriately used during each phase of the program.

Flyers by phase

NOTE: THESE ARE SAMPLES FROM BALTIMORE HEATHEY STORES AND BHEZ; THESE WILL NOT BE USED

PHASE 1 – HEALTHY BEVERAGES

PHASE 2: HEALTHY SNACKS

PHASE 3 – COOKING AT HOME/HEALTHY LUNCH AND BREAKFAST

PHASE 4 – DELI/CARRY-OUT

MATERIALS FOR STORE OWNERS

The interventionist will provide answers to frequently asked questions regarding the Maryland Healthy Stores project.  We are providing a schedule and document for the store owners in order to aid with implementation of the MHS program, called the MHS FAQ for Store Owners.

The MHS FAQ sheet in currently being developed.

STORE OWNER SCHEDULE

February – March            	Store and visits

Review of the program

April 25 – April 29	             Introduction of Interventionist

Interventionist comes and puts up posters for phase 0, gives store owner first wholesaler gift card (for phase 1 foods), discusses store stocking guidelines

Kickoff event will take place at some stores

May 5 -	June 3                           Phase 1 of the program (“Healthy Beverages”) begins

Interventionist puts up posters, shelf labels, begins taste tests

June 6 – July 8          	             Phase 2 Snacks

Interventionist takes down posters from previous phase and puts up new materials.  Conducts taste tests and activities for promoted items.

July 5 – August 12               	Phase 3 Cooking at home/Healthy lunch and breakfast

Interventionist takes down posters from previous phase and puts up new materials.  Conducts taste tests , cooking demonstrations, and other activities for promoted items.

August 15 – September 16	Phase 4 Healthy Deli/Carryout Foods

Interventionist takes down posters from previous phase and puts up new materials.  Conducts taste tests and activities for promoted items.

Interventionist will work with storeowner to come up with feasible methods to offer healthier foods (e.g., offer baked foods, veggie toppings and low-fat mayo).

Handout menus, which highlight healthy foods, will be provided to storeowners for distribution

INTERVENTIONIST WEEKLY PLANS

BY PHASE

Phase 0

Store Visit

- The lead interventionist visits each store with the assigned interventionist to introduce them and get them acquainted.

- Put up “Coming soon” posters when you visit your store.

- Check stocking of promoted beverages for phase 1, and provide stocking list highlighted to store owners.

- Corner store owners will be given a $50 Food Depot gift card for phase 1 to purchase promoted foods for phase 1. You must get a signed receipt for the gift card.

Phase 1: LOW CALORIE/LOW FAT BEVERAGES

Day 1 of Week 1 (Prep.)

Materials Needed

- Shelf Labels (LOW SUGAR, LOW FAT, HEALTHY CHOICE)

- Tape

- Phase 1 posters

- Phase 1 flyers

- Interventionist Log

Store Visit

- Put up the new Phase 1 posters in the store.

- Post MHS shelf labels under the appropriate diet sodas, water, fruit juices, crystal light, and milk etc.

- Inventory the current stock of sodas, fruit juices, crystal light, and water and encourage owners to stock the promoted sodas, juice drinks and water if not available for next week’s taste test.

- Introduce the idea of a soda, juice, and milk “taste tests” to the store owner. Coordinate with store owner on appropriate times and places to hold the taste tests.

- Give store owner flyers to include as shopping bag inserts

- Complete the Interventionist Log

Day 2 of Week 1- Week 3 (Low-sugar beverages)

Materials Needed

- Shelf Labels

- Tape

- Phase 1 Flyers

- Buttons

- Table

- Water bottle giveaways with inserted crystal light packages

- Taste-test materials

  - Table

  - Diet Sodas

  - Crystal Light packets mixed with 0.5 L water bottles

  - Dixie cups

  - Cooler and ice packs

  - Bottle filled with 16 tsp of sugar

- NCI document on artificial sweeteners

- Interventionist Log

Store Visit

- Before the visit, read over the MOP for taste-test specific instructions and materials needed.

- Check if posters are damaged, missing, etc and make note to replace if necessary.

- Post labels for any newly stocked beverages and check positioning of existing labels to ensure that they correspond with foods (in case they were moved).

- Check stocking of promoted beverages and encourage store owners to stock foods that are missing.

- Encourage owners to include flyers in shopping bags.

- Conduct taste-tests. See MOP for guidelines.

- Hand out flyers and buttons to customers to promote this phase.

- Give away water bottles with crystal light packets to only those customers who have an extended interaction with you.

- Complete the Interventionist Log

Photos: Please take photos of the stores—the shelf labels, posters, and taste-tests during all activities!

Week 4- Week 5 (Low-fat Milk)

Materials Needed

- Shelf Labels (same as mentioned above)

- Tape

- Phase 1 flyers

- Buttons

- Water bottles with inserted crystal light packages

- Taste-test materials

  - Table

  - Milk (whole, 2%, 1% and skim) for blind taste test

  - Dixie cups

  - Cooler and ice packs

- [Digital camera, if possible]

- Interventionist Log

Store Visit

- Walk through store to see if all MHS shelf labels and posters are posted and if food is stocked correctly.

- Inventory the current stock of newly stocked beverages and encourage owners to stock.

- Encourage owners to include flyers in shopping bags.

- Conduct the taste-test. Coordinate with store owner to find the best place in the store (back, front, anteroom, etc).

- Hand out flyers, buttons, and water bottles as described above.

- Complete the Interventionist Log.

- Clean up!

Phase 2: HEALTHY SNACKS

Day 1 of Week 1 (Prep.)

Materials Needed

- Shelf Labels (LOW FAT, HEALTHY CHOICE, LOWER IN SUGAR)

- Tape

- Phase 2 posters

- Phase 2 flyers

Store Visit

- Put up the new Phase 2 posters in the store.

- Post MHS food labels under the appropriate food items.

- Inventory the current stock of baked chips, fresh or canned fruit (in light syrup or 100% juice), seeds/nuts/trail mix, and granola bars, and encourage owners to stock the promoted foods if not available for next week’s activity.

- Give storeowners flyers for shopping bag inserts.

- Complete Interventionist Log

Day 2 of Week 1 onwards

Materials Needed

- Shelf Labels

- Tape

- Phase 2 Flyers

- Chip clip giveaways

- Buttons

- Magnets

- Taste-test materials

  - Table

  - Baked chips and pretzels

  - Fruit sample

  - Granola bar sample

  - Trail mix sample

  - Labeled dixie cups

- [Digital camera, if possible]

- Interventionist Log

Store Visit

- Check if posters are damaged, missing, etc and make note to replace if necessary.

- Post labels for any newly stocked foods and check positioning of existing labels to ensure that they correspond with foods (in case they were moved).

- Check stocking of promoted foods and encourage store owners to stock foods that are missing.

- Encourage store owners to include flyers in bags

- Conduct healthy snack taste tests.

- Hand out flyers, buttons, and magnets to customers to promote this phase and explain the messages of the phase.

- Distribute the chip clips at the same time, only to customers who have longer interactions

- Complete interventionist log.

- Clean-up

Photos: Please take photos of the stores—the shelf labels, posters, and taste-tests!

Phase 3: HEALTHY HOME FOOD PREPARATION

Day 1 of Week 1 (Prep.)

Materials Needed

- Shelf Labels (LOW FAT, HEALTHY CHOICE, HIGHER IN FIBER)

- Tape

- Phase 3 posters

- Phase 3 flyers

Store Visit

- Put up the new Phase 3 posters in the store.

- Post MHS food labels under the appropriate food and beverage (low-fat milk) items.

- Inventory the current stock of cooking spray, whole wheat bread, canned vegetables/or any vegetables (onion/potatoes), low-fat cheese (if feasible), low-fat mayo, and low-fat dressing, and encourage owners to stock the promoted foods if not available for next week’s activity.

- Distribute flyers to be inserted into bags.

- Inform the store owner about the uses of cooking spray, and the message that is being promoted in this phase. Coordinate with store owner on appropriate times and places to hold the intervention.

Day 2 of Week 1- onwards

Materials Needed

- Shelf Labels

- Tape

- Phase 3 Flyers

- Buttons

- Magnets

- Bowl giveaways

- Taste-test materials (weeks 1-3)

  - Table

  - Whole wheat bread

  - Low-fat cheese

  - Low-fat mayo

  - Low-fat dressing

  - Carrots

  - Paper plates

  - Dixie cups

  - Napkins

  - Cooler and ice packs

- Cooking demo materials (weeks 4-5)

  - Cooking spray

  - Hot plate/George Forman grill

  - Food for prep (TBD)

  - Paper plates

  - Napkins

  - Cooler and ice packs

- [Digital camera, if possible]

- Interventionist Log

Store Visit

- Check if posters are damaged, missing, etc and make note to replace if necessary.

- Post labels for any newly stocked foods and check positioning of existing labels to ensure that they correspond with foods (in case they were moved).

- Check stocking of promoted foods and encourage store owners to stock foods that are missing.

- Conduct taste tests (weeks 1-3).

- Conduct cooking demo (weeks 4-5)

- Encourage store owners to inserts flyers into shopping bags

- Handout flyers, buttons, and magnets to customers to promote this phase and explain the messages of the phase.

- Distribute the bowls at the same time, only to customers who have longer interactions.

- Complete interventionist log.

- Clean-up

Photos: Please take photos of the stores—the shelf labels, posters, and taste-tests!

Phase 4: HEALTHY DELI/CARRY-OUT

Day 1 of Week 1 (Prep.)

Materials Needed

- Shelf Labels (LOW FAT, HIGHER FIBER, HEALTHY CHOICE)

- Tape

- Phase 4 posters

- Phase 4 flyers

Store Visit

- Put up the new Phase 4 posters in the stores with delis/carryouts.

- Post MHS food labels under the appropriate food items.

- Give handout menus to storeowners for distribution.  These should be displayed on the deli/carryout countertop and in a plastic stand up plastic display cases.

- Inventory the current stock of low fat condiments (low fat mayo, mustard, ketchup) and whole wheat bread, and encourage owners to stock the promoted foods if not available for next week’s activity.

- Inform storeowners about our activities, and encourage them to prepare and promote our healthy alternatives.

Day 2 of Week 1 onwards

Materials Needed

- Shelf Labels

- Tape

- Phase 4 Flyers

- Buttons

- Magnets

- Light mayo packet giveaways

- Taste-test materials

  - Table

  - Sandwich materials (including light mayo) TBD

  - Paper plates

  - Napkins

  - Cooler and ice packs

- [Digital camera, if possible]

- Interventionist Log

Store Visit

- Check if posters are damaged, missing, etc and make note to replace if necessary.

- Check if menus (handouts) and POP display are intact and make note to replace if necessary.

- Post labels for any newly stocked foods and check positioning of existing labels to ensure that they correspond with foods (in case they were moved).

- Check stocking of promoted foods and encourage store owners to stock foods that are missing.

- Conduct sandwich with light mayo taste test.

- Handout flyers to customers to promote this phase and explain the messages of the phase. Distribute the giveaways at the same time.

- Complete the Interventionist Log

- Clean-up

Photos: Please take photos of the stores—the shelf labels, posters, and taste-tests!

COOKING

DEMONSTRATIONS

&

TASTE

TESTS

About cooking demos & taste tests

Conducting cooking demonstrations and taste tests

Cooking demonstrations/taste tests are one of the activities of the MHS Interventionist that takes up the greatest amount of his/her time. These activities will highlight the promoted foods and cooking methods for each phase of the MHS intervention, and will seek to engage youth and adults. Because several of the participating stores lack room for cooking demonstrations and taste tests, the interventionist will have to conduct them in spaces deemed appropriate by store owners.  Some store owners may request that these activities be conducted outside the store (i.e., the storefront).  Weather permitting, we should be wiling to conduct them wherever deemed appropriate by storeowners. The interventionist is responsible for making sure she/he has all needed materials (see tables that follow) ready before beginning a demonstration.

Timing

- Cooking demonstrations will only be conducted during the last 2 weeks of Phase 3, but they should be conducted 2 times per week in each store (a total of 4 times/store).  Taste tests will be conducted during each intervention, or 2 times a week for each store.

- Conduct demos at days/times of maximum attendance (i.e., during paydays, or during the lunch hour.).

Duration

Demonstrations should last approximately 1 hour in each store.

FOOD SAFETY

It is important to practice good food safety to prevent bacteria from getting into food or growing in food.  Bacteria can make you sick - like a stomachache, diarrhea, fever, throwing up, etc.  Steps to remember in keeping food safe:

            - Wash your hands thoroughly with soap and water, scrubbing all parts of your hands.  Use a paper towel to turn off the faucet.

            - Wash all fruits and vegetables before using.

            - Remember to keep foods cool or hot.  Raw or prepared foods should not be left out for more than two hours at room temperature. Use coolers and ice packs for milk, light mayo, salad dressing, etc.

            - Carry hand sanitizer for participants to use before and after trying the taste test.

DOCUMENTATION

The interventionist will need to document when and where cooking demos or taste tests were conducted.  The Interventionist Log will be used by the Interventionist to record when and where demos or taste tests were conducted.

Phase 1

Low calorie drinks and Low fat milk

LEARNING OBJECTIVES

1. Customers will taste test diet sodas, and sugar-free drink mixes

2. Consumers will do a blind taste-test of lower-fat milk.

3. Customers will observe the sugar content of a regular soda in a bottle filled with 16 tsp of sugar

4. Customers will be educated about the fat and nutrient content in each variety of milk

MATERIALS NEEDED

Dixie cups

20 oz. bottles of diet soda, Crystal Light packets, and 0.5 L water bottles

Whole and Low fat milk (2%, 1%, skim)

Cooler and ice packs

FLYERS/POSTERS (to be refined)

Water does the body good

After 2, you can go blue

Whole Milk is 50% fat

What are you really drinking?

EDUCATION DISPLAY

Quench your thirst with water

GIVEAWAYS

Water bottle with logo	 and crystal light inserts

Buttons

FREQUENTLY ASKED QUESTIONS

Q. Isn’t the stuff in diet soda bad for you?

A. No studies have shown that Nutrasweet (aspartame) increases risks of getting cancer or any other illness.  Note: Nutrasweet contains phenylalanine, which is dangerous for phenylketonurics (a genetic disease)

HAVE COPIES OF NCI DOCUMENT ON ARTIFICIAL SWEETENERS ON HAND, AND GIVE OUT TO CUSTOMERS WHO HAVE QUESTIONS.

Q. I thought diet soda is only for people with diabetes, sick people like that.

A. Diet pop is for anyone who wants to consume less sugar or calories. This includes diabetics, but can include any health-conscious person.  (Try to avoid the word “sick” here, especially in reference to diabetics.)

Q. Diet soda tastes funny to me… like it has chemicals in it.

A. All parts of foods are chemicals.  Sugar is a chemical.  Salt is a chemical.  Different chemicals, even when they are all natural, have different tastes.  The taste is a little different because it comes from something different.  But it’s safe to drink.  Many people actually prefer the taste of diet pop once they are used to them.  If you don't like the taste, water is another great alternative to soda.

Q. Don’t I need to buy whole milk if I receive WIC vouchers?

A. The WIC package changed in October 2009 so that stores are required to stock 1% or skim milk, so you should receive vouchers for those if your child is 2 years or older, or if you are pregnant or breastfeeding.

Q. Do low-fat and fat-free milk have less calcium and Vitamins D and A than whole milk?

A. No, actually lower fat milks have slightly more calcium and vitamins than whole milk. Since the fat content is reduced, there is more room for vitamins and minerals.

Q. I can’t drink skim milk—isn’t it just like water?

A. If you currently drink whole milk, you may want to first switch to 2% or 1%, and gradually reduce the fat content in your milk. If you currently drink 2%, you can try switching to 1% first.

| Activity #1 DIET POP/DRINKS TASTE TEST | Do soda taste test: 1. Provide 3-4 different types of diet soda giving a variety of tastes. Do not offer regular soda. 2. Alternatives to frequently consumed drinks: Diet Pepsi, Pepsi One, Diet Coke, Coke Zero, Sprite Zero, Diet 7UP, Diet ginger ale 3. Allow people to drink diet version of the soda they usually drink, and let them know that it is diet beforehand.. 4. Let people taste whichever ones they want. 5. Ask if they would drink any of these occasionally. |
| --- | --- |
| Activity #2 SUGAR IN REGULAR SODA DEMO | Do the sugar jar demonstration: 1 Show them the soda bottle filled with 16 tsp of sugar 2 Explain to customers that this represents the amount of sugar in 20 ounces of regular soda, and that this is equal to 16 tsp (or 16 packets) of sugar. |
| Activity #3 TALK ABOUT BENEFITS OF WATER | EMPHASIZE THAT WATER IS THE BEST CHOICE FOR A BEVERAGE Advantages of water: 1. Quenches your thirst 2. Helps maintain your body fluids so you perform better 3. Far cheaper and better for your health If people do not like the taste of their tap water suggest a filter. In areas where water quality is questionable, remind people they can boil the water. |
| Activity #4 SAMPLE LOWFAT MILK | Conduct the blinded taste test of milks: 1. Ask customer what kind of milk he/she usually drinks. 2. If they already drink 1% or skim, congratulate them and ask if other members of their household also drink the same milk. 3. If the consumer drinks skim, and other members of their household also drink skim, go to the giveaway. DON’T have them do the taste test – they can’t do better! 4. If the consumer drinks any other type of milk, then ask them to do a “blind taste test of different milks.” 5. If they are drinking 1%, they would only taste 1% and skim -- one Dixie cup each of1% and skim. 6. If they drink 2%, then have them taste one cup each of 2%, 1%, and skim. 7. If they normally drink whole, then they can taste one cup each of whole, 2%, 1%, and skim. Then instead of asking them which is the milk they usually drink, ask which they like the best. This will make an even bigger impression if they choose a lower-fat milk! 8. Behind a screen, mark the bottom of each cup with what kind of milk it has. (Note: you may wish to pre-mark several stacks of Dixie cups) 9. If they choose a lower-fat milk than they normally drink, then record their response as “PREFERS HEALTHY ALTERNATIVE” on the taste test chart using tick marks. If they choose their regular milk, then record this as “PREFERS USUAL CHOICE” on the taste test chart using tick marks. 10. In both cases, ask them, “what do you think of the lower fat milk?” “would you think about getting it in the future?” |

Phase 2

HEALTHY SNACKS

Learning objectives

- Consumers will taste-test baked / reduced fat chips and pretzels

- Consumers will taste-test or take home various fruits and vegetables

Materials needed

Baked chips/pretzels taste test:

Baked chips, baked tortilla chips, pretzels

Small baggies

Napkins

Fruit taste tests/giveaways

Various fruits (bananas, clementines, etc.)

Plastic bag for trash

Flyers/Posters

Baked is Better

Baked for better health

Baked vs. regular chips vs pretzels (TBD)

Strive for 5

How many fruits and vegetables have you had today?

Fill up with fiber (TBD)

Giveaways

Chip Clips

Magnets

Buttons

FREQUENTLY ASKED QUESTIONS

Q. Are baked chips healthier than regular chips? What about SunChips or tortilla chips?

A. Baked chips are lower in fat than regular chips since they are baked instead of fried. SunChips are slightly lower in fat than regular chips since they are made with sunflower oil, but they are still fried and have more fat than baked chips. Regular tortilla chips have about as much fat as regular potato chips, but baked tortilla chips are a healthier option. With any of these snacks, be sure to pay attention to the portion you’re eating—many bags of chips contain more than 1 serving , so it’s easy to eat more calories than recommended in one sitting.

Q. Don’t pretzels and chips have a lot of salt?

A. Yes, many packaged snacks are high in sodium. If you have high blood pressure or are worried about sodium/salt intake, you should avoid pretzels. They are lower in fat than regular chips, so they are a step in the right direction, but fruits and vegetables are still the healthiest options for snacks.

Q. Is this vegetable ice cream healthy for me?

A. Foods have many different components that contribute to being “healthy” or “unhealthy,” so it can sometimes be difficult to decide whether a food is “healthy”. This is still ice cream, so it’s slightly higher in fat and sugar than we usually recommend. But it has the vitamins and minerals from the vegetables it’s made with. It’s also an example of how you can present and prepare vegetables in new, fun ways.

| Activity #1 BAKED CHIP AND PRETZELS SAMPLES | - Provide samples of baked chips and pretzels in plastic bags for customers to try. - Compare the fat content of baked chips and pretzels to that of regular chips. |
| --- | --- |
| Activity #2 POTATO CHIP SMASH | - Crush regular potato chips into paper towels to show customers how much grease is in the chips |
| Activity #3 FRUIT SAMPLES | Provide samples of fruits (bananas, oranges, raisins) for customers to try. |
| Activity #4 GRANOLA/ TRAIL MIX SAMPLES | Provides samples of low-fat/low-sugar granola bars, and trail mix |

Phase 3

Healthy home food preparation

Learning objectives

Sandwich taste test:

- Participants will taste test whole wheat bread, low-fat mayo, and low-fat cheeses (in addition to low-fat poultry) on a sandwich

Cooking spray demo:

1. Consumers will see the cooking spray and learn about ways to use it for different foods.

2. Consumers will learn about the benefits of cooking spray (in terms of reducing intake of fat).

3. Consumers will see how to use cooking spray by observing and tasting a commonly eaten food prepared with spray instead of grease or oil.

Materials needed (sandwich taste test)

Whole wheat bread

Low-fat lunchmeat

Low-fat cheese

Low-fat mayonnaise

Tomatoes (cut before intervention) (TBD)

Small paper plates

Napkins

Gloves

Materials needed (carrot and low-fat dressing taste test)

Carrots

Low-fat ranch dressing

Dixie cups

Napkins

Gloves

Materials needed (cooking spray cooking demo)

Can of cooking spray

Associated food (TBD)

Portable griddle/hot plate/George Forman grill

Small paper plates

Napkins

Flyers/Posters

Forget the fried

Bake for better heath (TBD)

You are what you eat (TBD)

Eat more, die young (with single serving bowls)

Eat well, Stay strong, Live long (cooking spray flyer) (Old; TBD)

How many fruits and vegetables have you had today? (TBD)

Three ways to reduce fat at home (Old; TBD)

Giveaways

Portion size bowls

Measuring spoons

Buttons

Magnets

Frequently asked questions

Q. How long does a can of cooking spray last?

A. A can of cooking spray, depending on size, can be used 500-2000 times (that is for a quick spray).  If you use it a lot, it will still last for over a month.

Q. How does cooking spray taste?

A. Cooking sprays are just vegetable oil, so plain types don’t taste like anything much.  Go ahead and taste some of the flavored varieties we have here for you.

Q. Isn't cooking spray more expensive?

A. Well, a can of canola oil cooking spray has about 340 servings and costs about $3.89 (Safeway), so that is about 1cent per serving.  One serving of canola oil is 2 tsp. (10ml) so a $6.29 (Safeway 3000ml) bottle would hold about 300 servings which is about 2 cents a serving.  Margarine (Safeway) cost $3.09 for 907g, and a serving is about 2 tsp (10g), or about 3.4 cents.  There is a flyer which illustrates this as well.

Q. What are the different foods you can cook with cooking spray?

A.  Many of the foods you commonly prepare with grease or oil can be prepared with cooking spray.  These include stir-fry vegetables, meats, grilled sandwiches, fried eggs, or pancakes, anything that you might cook in a skillet. In terms of baked goods, the spray is for coating pans, and not a substitute for oil or shortening in the recipe.

Q. Is cooking spray safe to use?

A. Lecithin is a natural part of many foods, and all products in stores must be proven safe.

Q. What are the health benefits of using cooking spray?

A. When used according to the directions, cooking spray is calorie free, fat free and cholesterol free.

| Activity #1 SANDWICH TASTE TEST | - Wear gloves while removing bread and lunchmeat from packaging. - Ask customers whether they would like to try a cheese or lunchmeat (w/ or w/o cheese) sandwich (depending on what you have available) on whole wheat bread. Ask if they want low-fat mayo. - Prepare a ½ sandwich according to the way customer requests, and give it to them on a paper plate or napkin. - Explain the benefits of 100% whole wheat bread as compared to white bread (keeps you feeling full and provides longer-lasting energy, helps with digestion) - Explain the benefits (nutritional and economic) of packing a healthy lunch instead of buying carryout or fast food. - Explain the benefits of low-fat mayo vs. regular mayo - Explain the benefits of low-fat cheese vs. regular cheese |
| --- | --- |
| ACTIVITY #2 | - Squeeze a small amount (1-2T) of low-fat Ranch dressing into a Dixie cup. - Place 3-4 carrots in each cup, and give to interested customers. - Show them that low-fat ranch tastes just like regular without the fat (show them labels). - Emphasize the importance of getting adequate amounts of vegetables with each meal. |
| Activity #3 Cooking Spray demo | Food and methods are TBD |

Phase 4

HEALTHY DELI/CARRYOUT

Learning objectives

1. Consumers will see and taste healthier carry-out options.

2. Consumers will learn about the benefits of using whole wheat bread and less mayonnaise or light/low-fat mayonnaise (in terms of increasing fiber and reducing fat in foods)

3.	Consumers will taste-test whole wheat bread and light mayonnaise on a sandwich

Materials needed

Whole wheat bread

Light mayonnaise (squeeze bottle or packets)

Low-fat turkey or chicken deli meat

Low-fat cheese

Small plates

Napkins

Gloves

Flyers/Posters

Make healthy carryout choices

Hold the Mayo, your heart will love you (OLD; TBD))

Baked for better health (TBD)

You are what you eat

Giveaways

Buttons

Magnets

Individual packets of light mayo

Frequently asked questions

Q. What is fiber?

A. Fiber is found in plants.  For instance in a whole grain of wheat or rice, the thick outside part is fiber, or the stringy part of celery, that’s fiber.

Q. Why is fiber good for me?

A. Dietary fiber helps to move food through your intestines (and prevent constipation). It also makes you feel fuller so you eat less, and it takes longer to digest, so your blood sugar does not rise as quickly after eating a high fiber meal. In addition, it helps lower your blood cholesterol and prevent things like heart disease, some kinds of cancer, and diabetes.

Q. I guess I could try whole wheat bread, but my family won’t go for it.

A. If you don’t think they are ready for 100%, you can try 60% whole wheat first.  This still has more fiber than white bread.

Q. What about rye bread?

A. If it is made with whole rye grains, rye bread also has more fiber than white bread.

Q. Isn’t whole wheat bread more expensive?

A. Not always. For instance, at Safeway, the Safeway brand white, 60%, and 100% whole wheat loaves are all the same price.

| LIGHT MAYO/ WHOLE WHEAT BREAD ON SANDWICH TASTE TEST | Conduct the blinded taste test of mayonnaise: 1. Ask customer what condiments s/he usually puts on his/her sandwiches/subs and what kind of bread they usually eat 2. If they already use light mayonnaise, praise them and offer them a ½ sandwich on whole wheat bread with lunchmeat and light mayonnaise. 3. If the consumer uses regular mayonnaise, also have them try a ½ sandwich on whole wheat bread with lunchmeat and light mayonnaise 4. In both cases, ask them, “What do you think of the light mayonnaise?” “Would you think about getting it in the future?” - Ask them what they thought about the whole wheat bread they tried the mayonnaise on. - If they don’t usually eat whole wheat, ask them if they would try it in the future. - Explain that 100% whole wheat bread has twice the fiber of white bread and since most people don’t eat enough fiber at all, it’s important to eat high fiber foods. - Explain the benefits of low-fat mayonnaise. - Explain the benefits of low-fat cheese. - Explain the benefit of baked poultry (vs. fried. |
| --- | --- |

GIVEAWAYS
GIVEAWAYS

Giveaways are tangible incentives that serve an important reinforcing purpose.

Giveaways with the project logo include:

- MHS Refrigerator Magnet (All phases)

- MHS Buttons (All phases)

- MHS Flyers and Brochures (All phases)

- Water bottle with logo and “No Sugar Added” (Phase 1)

- Crystal Light On the Go Packets (Phase 1)

- Single Serving Bowls (Phase 3)

- Measuring Spoons (Phase 3)

- Chip Clips (Phase 2)

Other giveaways without the logo include:

- Sugar free drink mix (Crystal Light, etc.) packets (Phase 1, limited)

- Light mayo packets (Phase 3 and Phase 4)

FUNDING &

ADDITIONAL

RESOURCES
FUNDING RESOURCES

There are a many sources of funding for a variety of health promotion projects.  These may be a valuable tool in continuing promotion of health and well-being across your community. This section will identify funding sources and include some tips for applying for grants.

The American Diabetes Foundation http://professional.diabetes.org

This foundations primary goal is to make a unique contribution that will accelerate the search for the prevention and cure of diabetes and its complications.

The Atkinson Charitable Foundation www.atkinsonfoundation.ca

The Atkinson Foundation has early childhood development and economic justice programs.  These focus on evaluation of new strategies for improving health, education, and economic well-being.

Bell Community Support Fund http://www.truesportpur.ca/index.php/language/en/category/98

This fund helps communities promote inclusion and accessibility for hockey or soccer programs.  This could be through improving rink facilities or establishing equipment sharing programs or increasing coaching opportunities.  Grants are $5,000 or $25,000.

General Mills www.generalmills.com

Under the commitment section, General Mills offers grants for Youth Nutrition & Fitness as well as several other related areas.  For some grants affiliation with a Registered Dietician is required.  The program is administered from the United States, so applicants should investigate whether Canadian entities are eligible.

HBC Foundation www.hbc.com/hbc/socialresponsibility/foundation/

Grantee must be a registered charity or non-profit organization registered with Revenue Canada. Most bands are eligible to apply for such status if not already obtained.  HBC provides grants focused on Building Healthy Families, Creating Strong Communities, and Inspiring Young Canadians.

Laidlaw Foundation www.laidlawfdn.org

The Laidlaw Foundation funds three focus areas: art, youth, and environment.  The Youth Engagement program promotes involvement of youth in community decision making.  Past grantees have included groups in Northwest Ontario.

The Lawson Foundation http://www.lawson.on.ca/

The Lawson Foundation has a Healthy Communities Program, with grants for Diabetes.

# The Leonard and Helen R. Stulman Charitable Fundation

The Stulman Foundation supports programs in research and treatment for mental illness, aging, health care, and broad based charitable endeavors.

J. W. McConnell Family Foundation www.mcconnellfoundation.ca

The McConnell Foundation only makes grants to charities of non-profit organizations registered with Revenue Canada. It states that it “funds initiatives of national significance which address challenges for Canadian society by engaging people, by building resilient communities, and by developing a strong knowledge base for the work that we support.”  These may include local projects that address issues of national significance.  Its granting philosophy encourages innovative, collaborative, inclusive projects.

The McLean Foundation http://www.mcleanfoundation.on.ca/index.htm

The McLean Foundation provides support to a wide variety of projects in the arts, education, health, and general welfare with an “emphasis on projects showing promise of general social benefit but which may initially lack broad public appeal.”

The Moffat Family Fund

The Moffat Family Fund is administered by the Winnipeg Foundation www.wpgfdn.org but provides funds to communities in Northwest Ontario for project relating to community services, health, environment, education, recreation, arts, etc.

The Robert Wood Johnson Foundation Healthy Eating Research Program http://www.healthyeatingresearch.org/

The RWJF HER program supports research on environmental and policy strategies with strong potential to promote healthy eating among children to prevent childhood obesity, especially among low-income and racial and ethnic populations at highest risk for obesity.

Trillium Foundation http://www.trilliumfoundation.org/

The Trillium Foundation provides grants to communities and groups to help build healthier communities in Ontario.  Grants in the past have ranged from $5,000 to $300,000 for projects such as renovating ice rinks and tennis courts or organizing volunteer programs.  There are also useful tips and guidelines for grant preparation on this website.

This is just a taste of the many funding sources out there.  Corporations and local businesses also give grants to community projects.  Charity village has links to lists and databases of many more sources of funding for all kinds of projects: http://www.charityvillage.com/cv/ires/fund.asp.

Grant writing tips

One of the most important things before applying for a grant is to read the granting criteria VERY carefully to make sure your organization or proposal meets their requirements.

Things to consider:

- What is the concept?

- What is the need for this program?

- How will we carry out the program?

- What is our expected outcome? (i.e. number of participants, facility X built, increase in knowledge, etc.)

- How will we evaluate the program?

- What is the timeline?

- What will our expenses be?

According to the Foundation Center’s short course, answers to these questions can be organized along these lines in your proposal:

  - Executive Summary: umbrella statement for your case and summary of proposal

  - Statement of  Need: why is this project necessary

  - Project description: nuts and bolts of how project will be implemented and evaluated

  - Budget: financial description of project with explanatory notes

  - Organization information: history and governing structure of the organization, primary activities, audiences, and services

  - Conclusion: summary of proposal’s main points

For details on each of these sections, visit http://fdncenter.org/learn/shortcourse/prop1.html.

Here are some more resources for how to write a good grant proposal:

http://www.cpb.org/grants/grantwriting.html

http://www.mcf.org/mcf/grant/writing.htm

http://www.npguides.org/

http://www.proposalwriter.com/grants.html

ADDITIONAL RESOURCES

Below are websites with additional resources for health promotion and health activities.  MHS has not reviewed these materials and by listing them does not necessarily endorse them.

WEBSITES

Center for Training and Research Translation (see intervention; Baltimore Healthy Stores)

http://www.center-trt.org/index.cfm

5 a Day the Color Way

http://www.pbhfoundation.org/index.php

CATCH (Coordinated Approach to Child Health)

http://www.sph.uth.tmc.edu/catch/

Creating Healthy Kids

http://www.stonyfield.com/weblog/CreatingHealthyKids/index.html

Creative Wellness Solutions

http://www.actnowprogram.com/index_flash.asp

Health Promoting Schools

http://www.sofweb.vic.edu.au/hps/abouthps.htm

PE4Life

http://www.pe4life.org/

US Dept of Health and Human Services Center for Disease Control Physical Activity Resources

http://www.cdc.gov/nccdphp/dnpa/physical/index.htm

Smart-mouth

http://www.csoinet.org/smartmuth/bite.html

Victory Garden Movement

http://www.victorygardens.net/index.html

]

ARTICLES

Gittelsohn J, Franceschini MC, Rasooly I, Ries AV, Ho LS, Pavlovich W, Santos VT, Jennings S and Frick KD.  (2007) “Understanding the food environment in a low income urban setting: Implications for food store interventions,” Journal of Hunger & Environmental Nutrition, 2(2/3): 33-50.

Gittelsohn J, Suratkar S, Song H-J, Sacher S, Rajan R, Rasooly IR, Bednarek E, Sharma S and Anliker JA.  (2009) “Process evaluation of Baltimore Healthy Stores: A pilot health intervention program with supermarkets and corner stores in Baltimore City,” Health Promotion Practice, Jan 14. [Epub ahead of print].

Sharma S, Cao X, Arcan C, Mattingly M, Jennings S, Song HJ, Gittelsohn J, (2009) “Assessment of dietary intake in an inner-city African American population and development of a quantitative food frequency questionnaire to highlight foods and nutrients for a nutritional invention,” International Journal of Food Sciences and Nutrition, Apr 8:1-13. [Epub ahead of print]

Dodson J, Hsiao Y-C, Kasat M, Murray L, Nguyen N, Richards A and Gittelsohn J. (2009) “Formative research for a healthy diet intervention among inner-city adolescents:  The importance of family, school and neighborhood environment,” Ecology of Food and Nutrition, 48: 39-58.

Suratkar S*, Gittelsohn J, Song HJ*, Sharma S, Anliker JA, Mattingly M*, (2010) “Food insecurity is associated with food-related psychosocial factors and behaviors among low-income African American adults in Baltimore City,” Journal of Hunger and Environmental Nutrition, 5(1): 100-119.

Song HJ*, Gittelsohn J, Kim M, Suratkar S, Sharma S and Anliker JA, (2010) “Korean-American storeowners' perceived barriers and motivators for implementing a corner store-based nutrition program,” Health Promotion Practice, April 27 [Epub ahead of print].

Song HJ*, Gittelsohn J, Kim M, Suratkar S*, Sharma S, Anliker JA, and Mattingly M, “Korean American corner stores in Baltimore City: A key feature of the urban food environment,” (Manuscript submitted to Health Education and Behavior, March 2008).

Gittelsohn J, Song H-J, Suratkar S, Kumar M, Henry EG, Sharma S, Mattingly M, Anliker J, (2009) “An urban food store intervention positively impacts food-related psychosocial variables and food behaviors,” Health Education and Behavior, Nov 3. [Epub ahead of print].

Song HJ*, Gittelsohn J, Kim M, Suratkar S, Sharma S and Anliker JA, (2009) “A corner store intervention in a low-income urban community is associated with increased availability and sales of some healthy foods” Public Health Nutrition Apr 30:1-8. [Epub ahead of print].

D’Angelo H, Gittelsohn J, Suratkar S, Song HJ & Stauffer E. “Access and food source use are associated with healthy and unhealthy food purchasing behaviors among low-income African American adults in Baltimore City.” (Manuscript submitted to Public Health Nutrition, April 2010).

Surkan PJ, Coutinho AJ, Christiansen K, Dennisuk LA, Suratkar S, Mead E, Sharma S, Gittelsohn J. (2010) “Healthy food purchasing among African American youth, associations with child gender, adult caregiver characteristics and the home food environment,” Public Health Nutrition, Oct 5:1-8. [Epub ahead of print].

Gittelsohn J, Dennisuk LA, Christiansen K, Bhimani R, Johnson A, Alexander E, Lee M, Lee SH, Rowan M, and Coutinho A. “Development and implementation of Baltimore Healthy Eating Zones: A youth-centered intervention trial to improve the food environment around recreation centers in Baltimore City” (Manuscript submitted to Health Promotion Practice, November 2010).

Dennisuk LA, Coutinho AJ, Suratkar S, Surkan P, Christiansen K, Riley M, Anliker JA, Sharma S, Gittelsohn J. " Food expenditures and food purchasing among low-income urban African-American youth." (Manuscript submitted to AJPM, August 2010).

Coutinho AJ, Suratkar S, Dennisuk LA, Surkan PJ, Sharma S, Gittelsohn J. "Associations of youth and caregiver psychosocial factors and the home food environment with youth high-fat, high-sugar food-purchasing in low-income African American households" (Manuscript submitted to Health Education & Behavior, February 2010).

Lee SH, Rowan M, Powell L, Newman S, Anderson J, Klassen C, Frick K, Gittelsohn J. (2010) “Characteristics of prepared food sources in low-income neighborhoods of Baltimore City.” Ecology of Food and Nutrition, 49(6): 409-430.

PROCESS EVALUATION

PROCESS EVALUATION

An important part of the project is documenting how well the activities are carried out.  This is called process evaluation.  Much of this will be done by a trained process evaluator.  In addition, the interventionist will be responsible for keeping logs of activities.  The interventionist’s forms are located in Appendix A of this MOP.  Instructions for completion of each form are in the relevant section of the MOP. See Appendix A.

The interventionist will complete:

INTERVENTIONIST LOG

The process evaluator will complete:

PROCESS EVALUATION FORM will evaluate the availability of promoted foods, the placement of shelf labels, posters and educational displays.

INSTRUCTIONS FOR USE

The Process Evaluation Form will be used by the PE to record the stocking of food items and use of visual communication materials at participating stores.

- At the beginning of each phase, the PE should make a timeline to schedule store visits during the phase.  The PE should visit each store A MINIMUM OF TWICE per phase, which averages to once every month for a two-month phase.

- A new evaluation form should be filled out for each store at each visit.

- Complete the form in blue or black ink.

To fill out the form, the PE will follow these steps:

- Write the date and time.

- Write the promotional phase name and number, if known

- Write his/her name.

- Write the store name.

- Check the store type: corner store, carryout, or combined corner store/carryout. Fill out only the appropriate food availability section(s) based on the store type.

- Food availability

  - For each available food, count the number of items on the shelf and record in the “# items” space.

  - If there are more than 10 items for each food, write in “>10”

  - ALL FOOD ITEMS IN THE APPROPRIATE SECTION(S) (CORNER STORE/CARRYOUT) IN ALL PHASES SHOULD BE COMPLETED EVERY TIME.  For example, during phase 1, complete the food availability section for phases 1 through 5.

- Shelf labels

  - For each food, check ‘yes’ or ‘no’ for whether the appropriate shelf label is correctly positioned under the food.

  - Describe any problems with the condition or location of the labels in the “Comments” section.

  - SHELF LABELS SHOULD BE EVALUATED DURING THE CURRENT PHASE AND DURING EACH FOLLOWING PHASE.  For example, during phase 4, the shelf label section should be completed for phases 1 through 4.

- Posters

  - For each poster corresponding to the current phase, check ‘yes’ or ‘no’ for whether the poster is posted at the store.

  - Check ‘yes’ or ‘no’ for whether the poster is readily visible.

  - The poster section should only be completed for the current phase.  For example, during phase 3, only the phase 3 posters should be evaluated.

- Write any additional comments or complications.

- Write the store ID# on the top of each page if known. Otherwise, allow data manager to do this.

- Check the form to make sure all questions are answered completely and accurately.

INTERVENTIONIST LOG

INSTRUCTIONS FOR USE

The Interventionist Log will be used by the Interventionist to record the cooking demonstrations and taste tests.

- Complete this form in blue or black ink.  Do not leave any spaces blank.

- Turn in the original forms to the program coordinator in W2041.  Copies will be filed in a safe place.

To fill out the form, the interventionist will follow these steps:

- Write the date.

- Write his/her name.

- Check the correct venue.

- Write the name of the store, rec center, or carryout where the activities are done.

- Check the number of peer educators present.

- Check the correct promotional phase.

- Check whether it is the first visit of the phase or a follow-up visit, and whether you are posting materials (posters, shelf labels) and/or conducting a tatse test, cooking demo, or other activity.

- Write the time the activities start.

- Write the number of posters and shelf labels posted  (if none, write zero)

- Write the name or a description of the demo, taste test, or other activity.

- Make a tally mark for each time a person stops briefly at the table but does not participate (he/she may taste the food, but does not listen to the accompanying message or take a recipe/flyer).

- Make a tally mark for each time a person stops at the table and participates (he/she pays attention, tastes samples, takes recipes/flyers, asks questions, etc.)..

- Make a tally mark for each time you distribute a food sample or a person takes a food sample on his/her own.  At the end, count the tally marks and write the total number.

- Write the names of the flyers or print materials that are being distributed. Make a tally mark for each time you distribute each flyer/print material or a person takes one on his/her own.  At the end, count the tally marks and write the total number for each flyer/print material.  This can also be done by subtracting the number of left over flyers from the number you started out with to get the total.

- Write the types of giveaways that are being distributed. Make a tally mark for each time you distribute each giveaway.  At the end, count the tally marks and write the total number for each giveaway.  This can also be done by subtracting the number of left over items from the number you started out with to get the total.

- Write the time the cooking demo/taste test ends.

- Describe the participants’ reactions to the promoted products and intervention.

- Describe what people liked/didn’t like during the intervention activity.

- Describe what worked during the demo/taste test.  Use this space to describe factors such as outside factors affecting the demo, location and setup, or anything else that positively impacted the demo.

- Describe what do not go well during the demo/taste test.  Use this space to describe factors such as outside factors affecting the demo, location and setup, or anything else that negatively impacted the demo.

- Write any improvements that you think could be made to future demos/taste tests.

- Write any other comments that do not fit in the other spaces.

- Check the form to make sure all questions are answered completely and accurately.

APPENDIX A:

INTERVENTIONIST

LOG and PROCESS EVALUATION FORM

Data checked by: …………………..

Date of checking:…………………..

Data entered by: ………………….

Date of entry: ………………………

Form ID: …………..

Community ID:………..

FOR OFFICE USE ONLY

INTERVENTIONIST LOG

- Week ending:  ______/______/___________

- Interventionist name:

_______________________________________

- Venue:   ____ Store w/o Deli/Carryout      ____ Store w/ Deli/Carryout

- Number of  Peer Educators present:   ____ 0	   ____ 1       ____2         ____3

- PHASE:	____ 0 (Teaser)			____ 4 (Healthy snacks)

____ 1(Healthy beverages)   	____ 5 (Carryout foods)

____ 2 (Healthy breakfast)

____ 3 (Cooking at home)

| DATE (DD/MM/YY) | Activities Conducted (check all that apply) | MATERIALS POSTED IN STORE (#) |
| --- | --- | --- |
| / / | ____ 1st Visit of Phase ____ Follow-up Visit ____ Posting Materials ____ Cooking Demo/Taste Test ____ Other (_________________ ____________________________) | _____ Poster(s) Shelf Labels: _____ Higher in Fiber _____ Lower in Fat _____ Lower in Sugar _____ Healthy Choice |
| Start time: |  |  |
| Finish Time: |  |  |

____	Posting materials only (no interactive activities done) use p. 1 only

COOKING DEMO/TASTE TEST/EDUCATIONAL ACTIVITY LOG

- Type of cooking demonstration, taste test, or educational activity (e.g. diet soda/Crystal Light/LF milk taste test;): _______________________________________

- Start time:  _____:_____		4.   End time:   _____:_____

Calculate duration of activity after completion: _____ minutes

5.   Attendee Log (make tick marks to record as you go):

| Age of visitor | Brief visitors (10 sec – 1 min, just looking usually) |  | Longer visitors (>1 min, discussion) |  |
| --- | --- | --- | --- | --- |
|  | Male | Female | Male | Female |
| Young children (<10 years) |  |  |  |  |
| Older children 10-14 years) |  |  |  |  |
| Older teens (14-17 years) |  |  |  |  |
| Young adults (18-30 years) |  |  |  |  |
| Older adults (31+ years) |  |  |  |  |

6. Record Taste Test Response by Participants if applicable (make tick mark to note preference):

| Usual Choice | Healthy Alternative |
| --- | --- |
| TOTAL= | TOTAL= |

7.  Promotional Items. Indicate the food or giveaway type in parenthesis and use tick marks to record the number:

|  | NAME | TALLY | TOTAL |
| --- | --- | --- | --- |
| Food 1 |  |  |  |
| Food 2 |  |  |  |
| Food 3 |  |  |  |
| Flyer 1 |  |  |  |
| Flyer 2 |  |  |  |
| Flyer 3 |  |  |  |
| Giveaway 1 |  |  |  |
| Giveaway 2 |  |  |  |
| Giveaway 3 |  |  |  |

8. General Questions

What were reactions to the promoted products and intervention?

Which products did people like?

Which products people didn’t like?

What worked?

What didn’t work?

9. Frequently Asked Questions by participants:

10. Additional Comments

Data checked by: …………………..

Date of checking:…………………..

Data entered by: ………………….

Date of entry: ………………………

Form ID: …………..

Community ID:………..

MARYLAND HEALTHY STORES PROJECT

Process Evaluation Log

PHASE #: ______

NAME OF THE PHASE: _________________________________

Date: ____/_____/__________       		Time: __________ AM / PM (circle one)                                           Data Collector: ______________________________

Store Name: ___________________________________	Store ID: __________

1. Intervention Food List: Are the promoted foods available and labeled with MHS shelf label?

| Phase | Product | Available? (circle one) | Number available (#) | Varieties (#) | (Check One) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Label Correctly Placed | Label Incorrectly Placed | No Label |
| 1 | Water | Yes No |  |  |  |  |  |
| 1 | Diet Soda (e.g. Diet Coke, Coke Zero, Diet Pepsi, Pepsi One, Sprite Zero) | Yes No |  |  |  |  |  |
| 1 | Diet/Unsweetened Tea (_____________________) | Yes No |  |  |  |  |  |
| 1 | Crystal Light/Low Sugar Drink Mix | Yes No |  |  |  |  |  |
| 1 | Flavored Water (≤40 cal/serving) | Yes No |  |  |  |  |  |
| 1 | Everfresh 100% Orange Juice | Yes No |  | n/a |  |  |  |
| 1 | Other 100% Fruit Juice (___________________) | Yes No |  |  |  |  |  |
| 1 | Other 100% Fruit Juice (___________________) | Yes No |  |  |  |  |  |
| 2 | 2% Milk | Yes No |  |  |  |  |  |
| 2 | 1% or Skim Milk | Yes No |  |  |  |  |  |
| 2 | Cheerios | Yes No |  | n/a |  |  |  |
| 2 | Corn Flakes | Yes No |  | n/a |  |  |  |
| 2 | Grape Nuts | Yes No |  | n/a |  |  |  |
| 2 | Kix | Yes No |  | n/a |  |  |  |
| 2 | Special K | Yes No |  | n/a |  |  |  |
| 2 | Toasted Oats | Yes No |  | n/a |  |  |  |
| 2 | Total | Yes No |  | n/a |  |  |  |
| 2 | Wheat Chex | Yes No |  | n/a |  |  |  |
| 2 | Wheaties | Yes No |  | n/a |  |  |  |
| 2 | Other Low Sugar (<10 g sugar)/High Fiber Cereals (___________________) | Yes No |  |  |  |  |  |
| 2 | Other Low Sugar/High Fiber Cereals (___________________) | Yes No |  |  |  |  |  |
| 3 | Cooking Spray | Yes No |  |  |  |  |  |
| 4 | Apples | Yes No |  | n/a |  |  |  |
| 4 | Bananas | Yes No |  | n/a |  |  |  |
| 4 | Oranges | Yes No |  | n/a |  |  |  |
| 4 | Fruit Cup/Canned Fruit | Yes No |  |  |  |  |  |
| 4 | Baby Carrots | Yes No |  |  |  |  |  |
| 4 | Fresh Vegetables (___________________) | Yes No |  |  |  |  |  |
| 4 | Canned Vegetables (___________________) | Yes No |  |  |  |  |  |
| 4 | Frozen Vegetables (___________________) | Yes No |  |  |  |  |  |
| 4 | Frozen Fruits (___________________) | Yes No |  |  |  |  |  |
| 4 | Peanut Butter | Yes No |  |  |  |  |  |
| 5 | 100% Whole Wheat Bread | Yes No |  |  |  |  |  |
| 5 | Split Top Bread | Yes No |  |  |  |  |  |
| 5 | Light/fat-free Mayo | Yes No |  |  |  |  |  |
| 6 | Low Sodium Pretzels | Yes No |  |  |  |  |  |
| 6 | Baked/Reduced fat Chips (e.g. Lay’s Baked, Utz Baked, Utz DeLite, Sun Chips, Sunflower Chips, Reduced Fat Pringles) | Yes No |  |  |  |  |  |
| 6 | Low Fat/Low Sugar Granola Bars | Yes No |  |  |  |  |  |
| 6 | Nuts | Yes No |  |  |  |  |  |
| 6 | Low Sugar (no chocolate) Trail Mix | Yes No |  |  |  |  |  |
| 6 | Other Low Fat/Low Sugar Snacks (___________________) | Yes No |  |  |  |  |  |

Comments on availability or placement of shelf-labels:

2. Poster:

| Phase #/description of phase poster corresponds to | Title | Is the poster up? (circle one) | Is it visible? (circle one) |
| --- | --- | --- | --- |
|  |  | Yes No | Yes No |
|  |  | Yes No | Yes No |
|  |  | Yes No | Yes No |

Comments on the posters:

3. Nutrition Promotion Activities (taste-tests, health education, cooking demo., etc.):

| Type and description of activity | # of visitors/ participants | Type/# of giveaways distributed | Type/# promotional material distributed |
| --- | --- | --- | --- |

Additional Comments: